## Project tasks
Project name | TLD F&O and RED365 Project Plan
Plan owner | Ahmed Fawzy
Project start date | 2025-06-22 08:00
Project finish date | 2026-09-28 10:00
Duration | 331.13 days
% complete | 51%
Exported on | 2026-04-12 14:04
Task number | Outline number | Name | Depends on | Start | Finish | Duration | Assigned to | % complete | Effort | Effort completed | Effort remaining | Bucket | Dependents (after) | Milestone | Notes | Completed | Checklist Items | Labels | Priority | Sprint | Goal | end
1 | 1 | TLD Developments Phase 1(F&O and RED AR)) |  | 2025-06-22 08:00 | 2026-05-31 17:00 | 246 days |  | 73% | 1946 hours | 1020 hours | 926 hours |  |  | No |  |  |  |  | Medium
2 | 1.1 | Planning Phase |  | 2025-06-22 08:00 | 2025-07-02 17:00 | 9 days |  | 100% | 42 hours | 42 hours | 0 hours |  |  | No |  |  |  |  | Medium
3 | 1.1.1 | Prepare Draft Project Plan |  | 2025-06-22 08:00 | 2025-06-23 17:00 | 2 days |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 4FS, 5FS, 6FS, 7FS, 8FS, 9FS, 10FS | No |  |  |  |  | Medium | Backlog
4 | 1.1.2 | Onboarding & Preliminary Planning Meeting | 3FS | 2025-06-23 08:00 | 2025-06-23 17:00 | 1 day |  | 100% | 8 hours | 8 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
5 | 1.1.3 | Review Project Organization & Identify Stakeholders | 3FS | 2025-06-23 08:00 | 2025-06-23 17:00 | 1 day |  | 100% | 2 hours | 2 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
6 | 1.1.4 | Prepare Project Charter Document | 3FS | 2025-06-23 08:00 | 2025-06-23 17:00 | 1 day |  | 100% | 8 hours | 8 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
7 | 1.1.5 | Develop Project Risk Register | 3FS | 2025-06-23 08:00 | 2025-06-23 17:00 | 1 day |  | 100% | 8 hours | 8 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
8 | 1.1.6 | Develop Project Issue Log | 3FS | 2025-06-23 08:00 | 2025-06-23 10:00 | 0.13 days |  | 100% | 2 hours | 2 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
9 | 1.1.7 | Develop the Change Log | 3FS | 2025-06-23 08:00 | 2025-06-23 10:00 | 0.13 days |  | 100% | 2 hours | 2 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
10 | 1.1.8 | Resource Capacity Planning | 3FS | 2025-06-23 08:00 | 2025-06-23 17:00 | 1 day |  | 100% | 4 hours | 4 hours | 0 hours | Not Started | 11FS | No |  |  |  |  | Medium | Backlog
11 | 1.1.9 | Project Kick-off Meeting | 10FS | 2025-07-02 08:00 | 2025-07-02 17:00 | 1 day |  | 100% |  |  |  | Not Started | 32FS-6d, 33SS | No |  |  |  |  | Medium | Backlog
12 | 1.2 | Execution Stage |  | 2025-06-25 08:00 | 2025-10-22 17:00 | 86 days |  | 100% | 192 hours | 192 hours | 0 hours |  |  | No |  |  |  |  | Medium
13 | 1.2.1 | RED 365 Execution Activities |  | 2025-09-14 08:00 | 2025-10-22 17:00 | 29 days |  | 100% | 192 hours | 192 hours | 0 hours |  |  | No |  |  |  |  | Medium
14 | 1.2.1.1 | RED365 - CE Environment Preparation |  | 2025-09-14 08:00 | 2025-10-01 17:00 | 14 days |  | 100% | 88 hours | 88 hours | 0 hours |  |  | No |  |  |  |  | Medium
15 | 1.2.1.1.1 | License & Tenant Readiness | 50FS | 2025-09-14 08:00 | 2025-09-14 08:00 | 0 hours |  | 100% |  |  |  | Not Started | 16FS | Yes |  |  |  |  | Medium | Backlog
16 | 1.2.1.1.2 | Sandbox Envrionment Creation | 15FS | 2025-09-14 08:00 | 2025-09-19 17:00 | 40 hours |  | 100% | 40 hours | 40 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
17 | 1.2.1.1.3 | Master Data Orientation Sessions | 52FS+3d | 2025-09-23 08:00 | 2025-09-23 17:00 | 8 hours |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 18FS | No |  |  |  |  | Medium | Backlog
18 | 1.2.1.1.4 | Receive Master Data from Customer | 17FS | 2025-09-24 08:00 | 2025-09-29 17:00 | 32 hours |  | 100% | 24 hours | 24 hours | 0 hours | Not Started | 19FS | No |  |  |  |  | Medium | Backlog
19 | 1.2.1.1.5 | Upload Config. Data (Areas, Countries, Nationalities,…) | 18FS | 2025-09-30 08:00 | 2025-10-01 17:00 | 16 hours |  | 100% | 16 hours | 16 hours | 0 hours | Not Started | 21FS | No |  |  |  |  | Medium | Backlog
20 | 1.2.1.2 | Go-Through Preparation |  | 2025-10-02 08:00 | 2025-10-06 17:00 | 3 days |  | 100% | 24 hours | 24 hours | 0 hours |  |  | No |  |  |  |  | Medium
21 | 1.2.1.2.1 | Property mgt. Script | 19FS | 2025-10-02 08:00 | 2025-10-02 17:00 | 8 hours |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 22FS | No |  |  |  |  | Medium | Backlog
22 | 1.2.1.2.2 | Reservation, Contracting & Collection Script | 21FS | 2025-10-05 08:00 | 2025-10-06 17:00 | 16 hours |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 23FS | No |  |  |  |  | Medium | Backlog
23 | 1.2.1.2.3 | Admin User Script | 22FS | 2025-10-06 08:00 | 2025-10-06 17:00 | 8 hours |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 25FS | No |  |  |  |  | Medium | Backlog
24 | 1.2.1.3 | Go-Through Sessions |  | 2025-10-07 08:00 | 2025-10-22 17:00 | 12 days |  | 100% | 80 hours | 80 hours | 0 hours |  |  | No |  |  |  |  | Medium
25 | 1.2.1.3.1 | Property Management Go Through Session | 23FS | 2025-10-07 08:00 | 2025-10-07 17:00 | 8 hours |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 26FS | No |  |  |  |  | Medium | Backlog
26 | 1.2.1.3.2 | Reservation, Contracting & Collection Go Through Session | 25FS | 2025-10-08 08:00 | 2025-10-09 17:00 | 16 hours |  | 100% | 16 hours | 16 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
27 | 1.2.1.3.3 | Meeting Minutes Preparation |  | 2025-10-13 08:00 | 2025-10-16 17:00 | 32 hours |  | 100% | 32 hours | 32 hours | 0 hours | Not Started | 28FS | No |  |  |  |  | Medium | Backlog
28 | 1.2.1.3.4 | RED365 Gap Sheet Preparation | 27FS | 2025-10-19 08:00 | 2025-10-22 17:00 | 4 days |  | 100% | 24 hours | 24 hours | 0 hours | Not Started | 29FS | No |  |  |  |  | Medium | Backlog
29 | 1.2.1.3.5 | Red 365Conduct Fit Gap Workshop & Finalizing Fit-GAP Sheet | 28FS | 2025-10-22 08:00 | 2025-10-22 17:00 | 1 day |  | 100% |  |  |  | Not Started | 55FS | No |  |  |  |  | Medium | Backlog
30 | 1.2.2 | F&O Execution Activities |  | 2025-06-25 08:00 | 2025-09-16 17:00 | 60 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
31 | 1.2.2.1 | F&O Environment Preparation |  | 2025-06-25 08:00 | 2025-08-08 17:00 | 32 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
32 | 1.2.2.1.1 | Master Data Sheets Preparation | 11FS-6d | 2025-06-25 08:00 | 2025-06-26 17:00 | 16 hours |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
33 | 1.2.2.1.2 | Master Data Orientation | 11SS | 2025-07-02 08:00 | 2025-07-02 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 34FS | No |  |  |  |  | Medium | Backlog
34 | 1.2.2.1.3 | Receive Master Data | 33FS | 2025-07-14 08:00 | 2025-07-16 17:00 | 24 hours |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
35 | 1.2.2.1.4 | sandbox environment Preparation |  | 2025-07-27 08:00 | 2025-07-31 17:00 | 40 hours |  | 100% |  |  |  | Not Started | 36FS | No |  |  |  |  | Medium | Backlog
36 | 1.2.2.1.5 | Upload Master Data & Configuration | 35FS | 2025-07-31 08:00 | 2025-08-06 17:00 | 40 hours |  | 100% |  |  |  | Not Started | 37FS | No |  |  |  |  | Medium | Backlog
37 | 1.2.2.1.6 | UAT Environment Testing & Fine Tuning | 36FS | 2025-08-07 08:00 | 2025-08-08 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 39FS | No |  |  |  |  | Medium | Backlog
38 | 1.2.2.2 | Go-Through Preparation |  | 2025-08-11 08:00 | 2025-08-21 17:00 | 9 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
39 | 1.2.2.2.1 | Testing Scenarions Preparation | 37FS | 2025-08-11 08:00 | 2025-08-14 17:00 | 32 hours |  | 100% |  |  |  | Not Started | 40FS | No |  |  |  |  | Medium | Backlog
40 | 1.2.2.2.2 | Test Scripts Documents Preparation | 39FS | 2025-08-17 08:00 | 2025-08-21 17:00 | 40 hours |  | 100% |  |  |  | Not Started | 42FS | No |  |  |  |  | Medium | Backlog
41 | 1.2.2.3 | Go-Through Sessions |  | 2025-08-21 08:00 | 2025-09-16 17:00 | 19 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
42 | 1.2.2.3.1 | General Ledger | 40FS | 2025-08-21 08:00 | 2025-08-22 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 43FS | No |  |  |  |  | Medium | Backlog
43 | 1.2.2.3.2 | Accounts Payable & Accounts Receivable | 42FS | 2025-08-25 08:00 | 2025-08-26 17:00 | 16 hours |  | 100% |  |  |  | Not Started | 44FS | No |  |  |  |  | Medium | Backlog
44 | 1.2.2.3.3 | Budgeting | 43FS | 2025-08-27 08:00 | 2025-08-27 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 45FS | No |  |  |  |  | Medium | Backlog
45 | 1.2.2.3.4 | Cash & Bank Management & Tax | 44FS | 2025-08-28 08:00 | 2025-08-28 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 46FS | No |  |  |  |  | Medium | Backlog
46 | 1.2.2.3.5 | Fixed Assets | 45FS | 2025-08-31 08:00 | 2025-09-02 17:00 | 24 hours |  | 100% |  |  |  | Not Started | 47FS | No |  |  |  |  | Medium | Backlog
47 | 1.2.2.3.6 | procurement and sourcing | 46FS | 2025-09-02 08:00 | 2025-09-02 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 48FS | No |  |  |  |  | Medium | Backlog
48 | 1.2.2.3.7 | inventory | 47FS | 2025-09-03 08:00 | 2025-09-03 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 49FS | No |  |  |  |  | Medium | Backlog
49 | 1.2.2.3.8 | Project Management & Accounting | 48FS | 2025-09-04 08:00 | 2025-09-05 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 50FS | No |  |  |  |  | Medium | Backlog
50 | 1.2.2.3.9 | construction | 49FS | 2025-09-08 08:00 | 2025-09-08 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 51FS, 15FS | No |  |  |  |  | Medium | Backlog
51 | 1.2.2.3.10 | Service report delivery | 50FS | 2025-09-09 08:00 | 2025-09-11 17:00 | 24 hours |  | 100% |  |  |  | Not Started | 52FS, 53FS | No |  |  |  |  | Medium | Backlog
52 | 1.2.2.3.11 | Customer confirm service reports | 51FS | 2025-09-14 08:00 | 2025-09-16 17:00 | 24 hours |  | 100% |  |  |  | Not Started | 17FS+3d | No |  |  |  |  | Medium | Backlog
53 | 1.2.2.3.12 | F&O Gap Sheet Preparation | 51FS | 2025-09-14 08:00 | 2025-09-15 17:00 | 2 days |  | 100% |  |  |  | Not Started | 54FS | No |  |  |  |  | Medium | Backlog
54 | 1.2.2.3.13 | D365 Conduct Fit Gap Workshop & Finalizing Fit-GAP Sheet | 53FS | 2025-09-15 08:00 | 2025-09-15 17:00 | 8 hours |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
55 | 1.2.3 | Q-Gate Meeting & Phase Acceptance | 29FS | 2025-10-22 17:00 | 2025-10-22 17:00 | 0 days |  | 100% |  |  |  | Not Started | 59FS | Yes |  |  |  |  | Medium | Backlog
56 | 1.3 | Build & Deployment |  | 2025-06-22 08:00 | 2025-12-23 17:00 | 133 days |  | 100% |  |  |  |  | 104FS | No |  |  |  |  | Medium
57 | 1.3.1 | F&O Deployment Activities |  | 2025-10-23 08:00 | 2025-12-23 17:00 | 44 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
58 | 1.3.1.1 | Training & UAT Preparation |  | 2025-10-23 08:00 | 2025-11-03 17:00 | 8 days |  | 100% |  |  |  |  | 63FS | No |  |  |  |  | Medium
59 | 1.3.1.1.1 | Receive Final Master Data Sheets | 55FS | 2025-10-23 08:00 | 2025-10-27 17:00 | 24 hours |  | 100% |  |  |  | Not Started | 60FS, 61FS | No |  |  |  |  | Medium | Backlog
60 | 1.3.1.1.2 | UAT Configurations & Fine Tuning | 59FS | 2025-10-28 08:00 | 2025-11-03 17:00 | 40 hours |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
61 | 1.3.1.1.3 | Testing Scenarios & Test Scripts Updates | 59FS | 2025-10-28 08:00 | 2025-10-29 17:00 | 16 hours |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
62 | 1.3.1.2 | F&O Key User Training |  | 2025-11-04 08:00 | 2025-11-20 17:00 | 13 days |  | 100% |  |  |  |  | 73FS+15d | No |  |  |  |  | Medium
63 | 1.3.1.2.1 | General Ledger | 58FS | 2025-11-04 08:00 | 2025-11-05 17:00 | 16 hours |  | 100% |  |  |  | Not Started | 64FS | No |  |  |  |  | Medium | Backlog
64 | 1.3.1.2.2 | Accounts Payable & Accounts Receivable | 63FS | 2025-11-06 08:00 | 2025-11-07 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 65FS | No |  |  |  |  | Medium | Backlog
65 | 1.3.1.2.3 | Budgeting | 64FS | 2025-11-10 08:00 | 2025-11-10 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 66FS | No |  |  |  |  | Medium | Backlog
66 | 1.3.1.2.4 | Cash & Bank Management & Tax | 65FS | 2025-11-11 08:00 | 2025-11-11 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 67FS | No |  |  |  |  | Medium | Backlog
67 | 1.3.1.2.5 | Fixed Assets | 66FS | 2025-11-12 08:00 | 2025-11-13 17:00 | 16 hours |  | 100% |  |  |  | Not Started | 68FS | No |  |  |  |  | Medium | Backlog
68 | 1.3.1.2.6 | Project Management & Accounting | 67FS | 2025-11-16 08:00 | 2025-11-18 17:00 | 24 hours |  | 100% |  |  |  | Not Started | 69FS | No |  |  |  |  | Medium | Backlog
69 | 1.3.1.2.7 | Consilidation | 68FS | 2025-11-18 08:00 | 2025-11-18 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 70FS | No |  |  |  |  | Medium | Backlog
70 | 1.3.1.2.8 | Asset Leasing | 69FS | 2025-11-19 08:00 | 2025-11-19 17:00 | 8 hours |  | 100% |  |  |  | Not Started | 71FS | No |  |  |  |  | Medium | Backlog
71 | 1.3.1.2.9 | Financial Reporting | 70FS | 2025-11-20 08:00 | 2025-11-20 17:00 | 8 hours |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
72 | 1.3.1.3 | F&O Key User UAT |  | 2025-12-12 09:00 | 2025-12-23 17:00 | 8 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
73 | 1.3.1.3.1 | Budget General ledger Cash and Bank | 62FS+15d | 2025-12-12 09:00 | 2025-12-12 17:00 | 0 days |  | 100% |  |  |  | Not Started | 74FS+1d, 97FS+1d | Yes |  |  |  |  | Medium | Backlog
74 | 1.3.1.3.2 | Procure to pay | 73FS+1d | 2025-12-16 09:00 | 2025-12-16 17:00 | 1 day |  | 100% |  |  |  | Not Started | 75FS+3d | No |  |  |  |  | Medium | Backlog
75 | 1.3.1.3.3 | Construction | 74FS+3d | 2025-12-22 09:00 | 2025-12-22 17:00 | 1 day |  | 100% |  |  |  | Not Started | 76FS | No |  |  |  |  | Medium | Backlog
76 | 1.3.1.3.4 | Fixed assets - Accounts receivables | 75FS | 2025-12-23 09:00 | 2025-12-23 17:00 | 1 day |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
77 | 1.3.2 | Q-Gate Meeting & Phase Acceptance |  | 2025-06-22 08:00 | 2025-06-22 08:00 | 0 days |  | 100% |  |  |  | Not Started | 99FS, 103FS | Yes |  |  |  |  | Medium | Backlog
78 | 1.4 | Operation Stage |  | 2025-12-16 09:00 | 2026-05-31 17:00 | 119 days |  | 60% | 1712 hours | 786 hours | 926 hours |  |  | No |  |  |  |  | Medium
79 | 1.4.1 | RED365 Operation Activities (AR For F&O) |  | 2026-02-12 09:00 | 2026-05-07 17:00 | 61 days |  | 54% | 984 hours | 514 hours | 470 hours |  |  | No |  |  |  |  | Medium
80 | 1.4.1.1 | RED and F&O master data sheet Orientation |  | 2026-02-12 09:00 | 2026-02-16 17:00 | 3 days | Abdelrahman Faris, Shahdan Farouze | 100% | 48 hours | 48 hours | 0 hours | Not Started | 82FS, 81FS | No |  |  |  |  | Medium | Backlog
81 | 1.4.1.2 | License & Tenant Readiness | 80FS | 2026-02-17 09:00 | 2026-03-11 17:00 | 17 days | Ahmed Fawzy | 100% | 136 hours | 136 hours | 0 hours | Not Started | 82FS | No |  |  |  |  | Medium | Backlog
82 | 1.4.1.3 | RED365 - CE Production Environment Deployment & Configuration | 80FS, 81FS | 2026-03-12 09:00 | 2026-03-18 17:00 | 5 days | Rowan Omar | 100% | 40 hours | 40 hours | 0 hours | Not Started | 84FS | No |  |  |  |  | Medium | Backlog
83 | 1.4.1.4 | Receive Final Master Data (RED& F/O) |  | 2026-02-17 09:00 | 2026-04-12 17:00 | 39 days | Shahdan Farouze | 67% | 312 hours | 210 hours | 102 hours | Not Started | 84FS | No |  |  |  |  | Medium | Backlog
84 | 1.4.1.5 | Upload Master Data | 83FS, 82FS | 2026-04-06 09:00 | 2026-04-14 17:00 | 7 days | Abdelrahman Faris, Sohila Hossam Eldin Youssef | 14% | 32 hours | 16 hours | 16 hours | Not Started | 85FS, 88FS | No |  |  |  |  | Medium | Backlog
85 | 1.4.1.6 | Receive Historical Transactional Data (RED365) | 84FS | 2026-04-14 17:00 | 2026-04-14 17:00 | 0 days | Shahdan Farouze | 0% |  |  |  | Not Started | 88FS | Yes |  |  |  |  | Medium | Backlog
86 | 1.4.1.7 | EOI go-through session + preparation |  | 2026-04-08 09:00 | 2026-04-12 13:00 | 2.5 days | Shahdan Farouze | 0% | 12 hours | 0 hours | 12 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
87 | 1.4.1.8 | PA to F&O Integration Readiness |  | 2026-04-01 09:00 | 2026-04-19 17:00 | 13 days | # Mahmoud Adel, Shahdan Farouze, Abdelrahman Faris | 54% | 104 hours | 64 hours | 40 hours | Not Started | 90FS, 89FS | No |  |  |  |  | Medium | Backlog
88 | 1.4.1.9 | Upload Historical Data | 85FS, 84FS | 2026-04-15 09:00 | 2026-04-21 17:00 | 5 days | Abdelrahman Faris | 0% | 100 hours | 0 hours | 100 hours | Not Started | 95FS | No |  |  |  |  | Medium | Backlog
89 | 1.4.1.10 | F&O Package deployment + Plugin Deployment | 87FS | 2026-04-19 17:00 | 2026-04-20 17:00 | 1 day | Mahmoud Radwan | 0% |  |  |  | Not Started | 90FS, 91FS | No |  |  |  |  | Medium | Backlog
90 | 1.4.1.11 | RED integration plugin Deployment + Workflows and | 87FS, 89FS | 2026-04-20 17:00 | 2026-04-21 17:00 | 1 day | Rowan Omar | 0% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
91 | 1.4.1.12 | Full Process Go-Through (RED-F&O) | 89FS | 2026-04-20 17:00 | 2026-04-21 17:00 | 1 day | Shahdan Farouze, # Mahmoud Adel | 0% |  |  |  | Not Started | 92FS, 95FS, 137FS | No |  |  |  | Yellow | Medium | Backlog
92 | 1.4.1.13 | Training (RED-F&O) | 91FS | 2026-04-22 09:00 | 2026-04-23 17:00 | 2 days | Shahdan Farouze, # Mahmoud Adel | 0% | 16 hours | 0 hours | 16 hours | Not Started | 95FS, 137FS | No |  |  |  | Yellow | Medium | Backlog
93 | 1.4.1.14 | EOI & Leads Training Session |  | 2026-04-14 09:00 | 2026-04-14 17:00 | 1 day | Abdelrahman Faris | 0% | 8 hours | 0 hours | 8 hours | Not Started | 94FS | No |  |  |  |  | Medium | Backlog
94 | 1.4.1.15 | EOI&Leads Live Support (RED only) | 93FS | 2026-04-15 09:00 | 2026-04-16 17:00 | 2 days | Abdelrahman Faris | 0% | 16 hours | 0 hours | 16 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
95 | 1.4.1.16 | Backlog Historical data syncing AR | 88FS, 92FS, 91FS | 2026-04-24 09:00 | 2026-05-07 17:00 | 10 days | # Mahmoud Adel, Lamis Rady | 0% | 160 hours | 0 hours | 160 hours | Not Started | 112FS | No |  |  |  |  | Medium | Backlog
96 | 1.4.2 | F&O Operation Activities |  | 2025-12-16 09:00 | 2026-05-06 17:00 | 102 days |  | 75% | 352 hours | 272 hours | 80 hours |  |  | No |  |  |  |  | Medium
97 | 1.4.2.1 | Microsoft Fast Track Assessment & Go-Live readiness | 73FS+1d | 2025-12-16 09:00 | 2026-01-29 17:00 | 264 hours |  | 100% |  |  |  | Not Started | 98FS, 100FS | No |  |  |  |  | Medium | Backlog
98 | 1.4.2.2 | F&O Production Environment Deployment & Configuration | 97FS | 2026-03-02 09:00 | 2026-03-08 17:00 | 40 hours | Moaaz Yassin | 100% | 40 hours | 40 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
99 | 1.4.2.3 | Receive Final Master Data | 77FS | 2026-02-17 09:00 | 2026-03-08 17:00 | 112 hours | # Mahmoud Adel | 100% | 112 hours | 112 hours | 0 hours | Not Started | 100FS | No |  |  |  |  | Medium | Backlog
100 | 1.4.2.4 | Upload Master Data and Conf the Prod | 99FS, 97FS | 2026-03-09 09:00 | 2026-03-17 17:00 | 56 hours | Sohila Hossam Eldin Youssef, # Mahmoud Adel | 100% | 112 hours | 112 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
101 | 1.4.2.5 | Delivery Opening Balance Sheet |  | 2026-03-04 09:00 | 2026-04-02 17:00 | 176 hours |  | 100% |  |  |  | Not Started | 103FS | No |  |  |  |  | Medium | Backlog
102 | 1.4.2.6 | Review Opening Balance Sheets |  | 2026-04-05 09:00 | 2026-04-06 17:00 | 2 days | Sohila Hossam Eldin Youssef | 100% | 8 hours | 8 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
103 | 1.4.2.7 | Upload Opening Balance Sheet | 77FS, 101FS | 2026-04-07 09:00 | 2026-04-13 17:00 | 5 days | # Mahmoud Adel, Sohila Hossam Eldin Youssef | 0% | 80 hours | 0 hours | 80 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
104 | 1.4.2.8 | F&O Soft Go-live(Except AR) | 56FS | 2026-04-19 09:00 | 2026-04-19 09:00 | 0 hours |  | 0% |  |  |  | Not Started | 112FS | Yes |  |  |  |  | Medium | Backlog
105 | 1.4.2.9 | Legal Entities rollout (Non TLD) |  | 2026-04-14 09:00 | 2026-05-06 17:00 | 17 days |  | 0% | [5 empty] | No |  |  |  |  | Medium
106 | 1.4.2.9.1 | Receive Final Master Data |  | 2026-04-14 09:00 | 2026-04-20 17:00 | 5 days |  | 0% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
107 | 1.4.2.9.2 | Upload Master Data and Conf the Prod |  | 2026-04-19 09:00 | 2026-04-23 17:00 | 5 days |  | 0% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
108 | 1.4.2.9.3 | Delivery Opening Balance Sheet |  | 2026-04-23 09:00 | 2026-04-29 17:00 | 5 days |  | 0% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
109 | 1.4.2.9.4 | Review Opening Balance Sheets |  | 2026-04-28 09:00 | 2026-04-29 17:00 | 2 days |  | 0% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
110 | 1.4.2.9.5 | Upload Opening Balance Sheet |  | 2026-04-30 09:00 | 2026-05-06 17:00 | 5 days |  | 0% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
111 | 1.4.3 | Go-live |  | 2026-05-08 09:00 | 2026-05-31 17:00 | 16 days |  | 0% | 376 hours | 0 hours | 376 hours |  |  | No |  |  |  |  | Medium
112 | 1.4.3.1 | Go-Live | 104FS, 95FS | 2026-05-08 09:00 | 2026-05-10 17:00 | 1 day | # Mahmoud Adel, Shahdan Farouze | 0% | 16 hours | 0 hours | 16 hours | Not Started | 113FS | No |  |  |  |  | Medium | Backlog
113 | 1.4.3.2 | Go-Live Support | 112FS | 2026-05-11 09:00 | 2026-05-31 17:00 | 120 hours | # Mahmoud Adel, Shahdan Farouze, Sohila Hossam Eldin Youssef | 0% | 360 hours | 0 hours | 360 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
114 | 2 | TLD RED Developments Phase 2 (New RED scope) |  | 2026-01-28 09:00 | 2026-09-28 10:00 | 173.13 days |  | 23% | 1750 hours | 354 hours | 1396 hours |  |  | No |  |  |  |  | Medium
115 | 2.1 | Planning Phase |  | 2026-01-28 09:00 | 2026-02-08 12:00 | 7.38 days |  | 100% | [5 empty] | No |  |  |  |  | Medium
116 | 2.1.1 | Onboarding& Preliminary Planning Meeting |  | 2026-01-28 09:00 | 2026-01-29 10:00 | 1.13 days |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
117 | 2.1.2 | Review Project Organization& Identify Stakeholders |  | 2026-02-02 10:00 | 2026-02-03 11:00 | 1.13 days |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
118 | 2.1.3 | Prepare Draft Project Plan |  | 2026-02-02 09:00 | 2026-02-03 10:00 | 1.13 days |  | 100% |  |  |  | Not Started | 122FS, 119FS, 120FS, 121FS, 123FS | No |  |  |  |  | Medium | Backlog
119 | 2.1.4 | Develop Project Risk Register | 118FS | 2026-02-03 10:00 | 2026-02-04 11:00 | 1.13 days |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
120 | 2.1.5 | Develop Project Issue Log | 118FS | 2026-02-03 10:00 | 2026-02-03 12:00 | 0.25 days |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
121 | 2.1.6 | Develop the Change Log | 118FS | 2026-02-03 10:00 | 2026-02-03 12:00 | 0.25 days |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
122 | 2.1.7 | Prepare Project Charter Document | 118FS | 2026-02-03 10:00 | 2026-02-04 11:00 | 1.13 days |  | 100% |  |  |  | Not Started |  | No |  |  |  |  | Medium | Backlog
123 | 2.1.8 | Resource Capacity Planning | 118FS | 2026-02-03 10:00 | 2026-02-04 11:00 | 1.13 days |  | 100% |  |  |  | Not Started | 124FS | No |  |  |  |  | Medium | Backlog
124 | 2.1.9 | Project Kick-off Meeting | 123FS | 2026-02-08 11:00 | 2026-02-08 12:00 | 0.13 days |  | 100% |  |  |  | Not Started | 131FS, 129FS | No |  |  |  |  | Medium | Backlog
125 | 2.2 | RED365 Plan |  | 2026-02-09 09:00 | 2026-08-19 13:00 | 137.5 days |  | 24% | 1530 hours | 354 hours | 1176 hours |  |  | No |  |  |  |  | Medium
126 | 2.2.1 | Execution Stage |  | 2026-02-09 09:00 | 2026-05-27 17:00 | 78 days |  | 33% | 470 hours | 218 hours | 252 hours |  |  | No |  |  |  |  | Medium
127 | 2.2.1.1 | RED 365 Execution Activities |  | 2026-02-09 09:00 | 2026-05-26 15:00 | 76.75 days |  | 33% | 461 hours | 218 hours | 243 hours |  |  | No |  |  |  |  | Medium
128 | 2.2.1.1.1 | RED365 - CE Environment Preparation |  | 2026-02-09 09:00 | 2026-04-05 14:00 | 39.63 days |  | 46% | 298 hours | 218 hours | 80 hours |  | 137FS | No |  |  |  |  | Medium
129 | 2.2.1.1.1.1 | Master Data Preparation | 124FS | 2026-02-09 09:00 | 2026-02-11 14:00 | 2.63 days |  | 100% | 16 hours | 16 hours | 0 hours | Not Started | 130FS | No | Customers, Units, Projects, PC, Property Hierarchy |  |  |  | Medium | Backlog
130 | 2.2.1.1.1.2 | Master Data Orientation Sessions | 129FS | 2026-02-12 14:00 | 2026-02-16 14:00 | 2 days |  | 100% | 16 hours | 16 hours | 0 hours | Not Started | 135FS | No |  |  |  |  | Medium | Backlog
131 | 2.2.1.1.1.3 | License & Tenant Readiness | 124FS | 2026-02-09 09:00 | 2026-02-22 17:00 | 10 days |  | 100% | 80 hours | 80 hours | 0 hours | Not Started | 133FS, 134FS, 132FS | No |  |  |  |  | Medium | Backlog
132 | 2.2.1.1.1.4 | Admin Role Readiness | 131FS | 2026-03-15 09:00 | 2026-03-15 09:00 | 0 days |  | 100% |  |  |  | Not Started | 133FS | Yes |  |  |  |  | Medium | Backlog
133 | 2.2.1.1.1.5 | Sandbox Envrionment Creation & Deployment | 131FS, 132FS | 2026-03-15 09:00 | 2026-03-30 17:00 | 12 days |  | 100% | 88 hours | 88 hours | 0 hours | Not Started | 134FS | No |  |  |  |  | Medium | Backlog
134 | 2.2.1.1.1.6 | Upload Config. Data (Areas, Countries, Nationalities,…) | 131FS, 133FS | 2026-03-31 09:00 | 2026-04-02 14:00 | 2.63 days |  | 100% | 18 hours | 18 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
135 | 2.2.1.1.1.7 | Master Data/Historical Data Receiving (Customer) | 130FS | 2026-02-16 14:00 | 2026-04-05 14:00 | 34 days |  | 0% | 80 hours | 0 hours | 80 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
136 | 2.2.1.1.2 | Go-Through Sessions |  | 2026-04-07 11:00 | 2026-05-12 10:00 | 24.88 days |  | 0% | 84 hours | 0 hours | 84 hours |  | 193FS, 185FS | No |  |  |  |  | Medium
137 | 2.2.1.1.2.1 | Property Management Go Through Session | 128FS, 91FS, 92FS | 2026-04-26 09:00 | 2026-04-27 12:00 | 1.38 days |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 138FS | No |  |  |  |  | Medium | Backlog
138 | 2.2.1.1.2.2 | Sales Management Go Through Sessions | 137FS | 2026-04-27 12:00 | 2026-04-30 10:00 | 2.75 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started | 139FS+2d | No |  |  |  |  | Medium | Backlog
139 | 2.2.1.1.2.3 | Property & Sales Meeting Minutes Preparation | 138FS+2d | 2026-05-04 10:00 | 2026-05-06 11:00 | 2.13 days |  | 0% | 12 hours | 0 hours | 12 hours | Not Started | 142FS | No |  |  |  |  | Medium | Backlog
140 | 2.2.1.1.2.4 | Basic Marketing/Customer insights Journey Go-Through |  | 2026-04-07 11:00 | 2026-04-09 17:00 | 2.75 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started | 141FS | No |  |  |  |  | Medium | Backlog
141 | 2.2.1.1.2.5 | Marketing Meeting Minutes Preparation | 140FS | 2026-04-12 09:00 | 2026-04-13 15:00 | 1.75 days |  | 0% | 8 hours | 0 hours | 8 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
142 | 2.2.1.1.2.6 | Delivery Management Go-Through Session | 139FS | 2026-05-06 11:00 | 2026-05-06 15:00 | 0.5 days |  | 0% | 4 hours | 0 hours | 4 hours | Not Started | 143FS | No |  |  |  |  | Medium | Backlog
143 | 2.2.1.1.2.7 | Client Relations Go-Through Session | 142FS | 2026-05-06 15:00 | 2026-05-07 15:00 | 1 day |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 144FS | No |  |  |  |  | Medium | Backlog
144 | 2.2.1.1.2.8 | Client Excellence Meeting Minutes Preparation | 143FS | 2026-05-07 15:00 | 2026-05-12 10:00 | 2.38 days |  | 0% | 12 hours | 0 hours | 12 hours | Not Started | 146FS | No |  |  |  |  | Medium | Backlog
145 | 2.2.1.1.3 | GAP FIT/GAP |  | 2026-05-12 10:00 | 2026-05-26 15:00 | 10.63 days |  | 0% | 79 hours | 0 hours | 79 hours |  |  | No |  |  |  |  | Medium
146 | 2.2.1.1.3.1 | Gap Sheet Preparation RED | 144FS | 2026-05-12 10:00 | 2026-05-17 17:00 | 3.88 days |  | 0% | 25 hours | 0 hours | 25 hours | Not Started | 147FS, 152FS | No |  |  |  |  | Medium | Backlog
147 | 2.2.1.1.3.2 | Conduct Fit Gap Workshop& Finalizing Fit-GAP Sheet Red | 146FS | 2026-05-18 09:00 | 2026-05-19 15:00 | 1.75 days |  | 0% | 14 hours | 0 hours | 14 hours | Not Started | 148FS | No |  |  |  |  | Medium | Backlog
148 | 2.2.1.1.3.3 | Gap Sheet sizing & estimation RED | 147FS | 2026-05-19 15:00 | 2026-05-26 15:00 | 5 days |  | 0% | 40 hours | 0 hours | 40 hours | Not Started | 149FS, 178FS | No |  |  |  |  | Medium | Backlog
149 | 2.2.1.2 | Q-Gate Meeting& Phase Acceptance RED | 148FS | 2026-05-26 15:00 | 2026-05-27 17:00 | 1.25 days |  | 0% | 9 hours | 0 hours | 9 hours | Not Started | 157FS, 175FS | No |  |  |  |  | Medium | Backlog
150 | 2.2.2 | Build& Deployment |  | 2026-04-13 14:00 | 2026-07-27 10:00 | 74.5 days |  | 21% | 929 hours | 136 hours | 793 hours |  |  | No |  |  |  |  | Medium
151 | 2.2.2.1 | RED365 GAP Points Development (show stopper for Go-Live) |  | 2026-05-18 09:00 | 2026-05-31 16:00 | 9.88 days |  | 0% | 68 hours | 0 hours | 68 hours |  | 157FS, 193FS | No |  |  |  |  | Medium
152 | 2.2.2.1.1 | Unit Hold/Release Request WF | 146FS | 2026-05-18 09:00 | 2026-05-20 13:00 | 2.5 days |  | 0% | 20 hours | 0 hours | 20 hours | Not Started | 153FS | No |  |  |  |  | Medium | Backlog
153 | 2.2.2.1.2 | Maintenance Calculation Configuration | 152FS | 2026-05-20 13:00 | 2026-05-26 10:00 | 3.63 days |  | 0% | 29 hours | 0 hours | 29 hours | Not Started | 154FS | No |  |  |  |  | Medium | Backlog
154 | 2.2.2.1.3 | Contract Cancelation/Termination Form SSRS | 153FS | 2026-05-26 10:00 | 2026-05-28 11:00 | 2.13 days |  | 0% | 11 hours | 0 hours | 11 hours | Not Started | 155FS | No |  |  |  |  | Medium | Backlog
155 | 2.2.2.1.4 | Customer Go-Through Session on Gap points developed | 154FS | 2026-05-28 11:00 | 2026-05-31 16:00 | 1.63 days |  | 0% | 8 hours | 0 hours | 8 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
156 | 2.2.2.2 | RED to RED Integration |  | 2026-05-31 16:00 | 2026-06-28 12:00 | 19.5 days |  | 0% | 146 hours | 0 hours | 146 hours |  | 162FS, 193FS | No |  |  |  |  | Medium
157 | 2.2.2.2.1 | PA - Dyn Integration RED TO RED (Property Module) | 149FS, 151FS | 2026-05-31 16:00 | 2026-06-04 16:00 | 4 days |  | 0% | 26 hours | 0 hours | 26 hours | Not Started | 158FS | No |  |  |  |  | Medium | Backlog
158 | 2.2.2.2.2 | PA - Dyn Integration RED TO RED (Sales/Mkt. Modules) | 157FS | 2026-06-04 16:00 | 2026-06-15 12:00 | 6.5 days |  | 0% | 50 hours | 0 hours | 50 hours | Not Started | 159FS | No |  |  |  |  | Medium | Backlog
159 | 2.2.2.2.3 | PA - Dyn Integration RED TO RED (Client Relations Module) | 158FS | 2026-06-15 12:00 | 2026-06-28 12:00 | 9 days |  | 0% | 70 hours | 0 hours | 70 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
160 | 2.2.2.3 | Other Integrations in Scope |  | 2026-04-13 14:00 | 2026-07-09 15:00 | 63.13 days |  | 40% | 456 hours | 136 hours | 320 hours |  | 193FS | No |  |  |  |  | Medium
161 | 2.2.2.3.1 | SharePoint Integration |  | 2026-05-14 15:00 | 2026-05-31 15:00 | 11 days |  | 9% | 88 hours | 8 hours | 80 hours |  | 165FS | No |  |  |  |  | Medium
162 | 2.2.2.3.1.1 | Customer to create SharePoint site and send it | 156FS | 2026-05-14 15:00 | 2026-05-17 15:00 | 1 day |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 163FS | No |  |  |  |  | Medium | Backlog
163 | 2.2.2.3.1.2 | SharePoint Integration Development | 162FS | 2026-05-17 15:00 | 2026-05-31 15:00 | 10 days |  | 0% | 80 hours | 0 hours | 80 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
164 | 2.2.2.3.2 | Zapier Integration |  | 2026-05-31 15:00 | 2026-06-11 17:00 | 9.25 days |  | 0% | 72 hours | 0 hours | 72 hours |  | 167FS | No |  |  |  |  | Medium
165 | 2.2.2.3.2.1 | Zapier License Readiness (Customer) | 161FS | 2026-05-31 15:00 | 2026-06-01 17:00 | 1.25 days |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 166FS | No |  |  |  |  | Medium | Backlog
166 | 2.2.2.3.2.2 | Zapier Integration Development | 165FS | 2026-06-02 09:00 | 2026-06-11 17:00 | 8 days |  | 0% | 64 hours | 0 hours | 64 hours | Not Started | 169FS | No |  |  |  |  | Medium | Backlog
167 | 2.2.2.3.3 | Website Integration Expose APIs | 164FS | 2026-06-14 09:00 | 2026-06-15 17:00 | 2 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
168 | 2.2.2.3.4 | SMS Integration |  | 2026-06-14 09:00 | 2026-06-24 11:00 | 8.25 days |  | 0% | 66 hours | 0 hours | 66 hours |  | 172FS | No |  |  |  |  | Medium
169 | 2.2.2.3.4.1 | SMS Gateway Readiness (Customer) | 166FS | 2026-06-14 09:00 | 2026-06-14 17:00 | 1 day |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 170FS | No |  |  |  |  | Medium | Backlog
170 | 2.2.2.3.4.2 | SMS Integration Development | 169FS | 2026-06-15 09:00 | 2026-06-24 11:00 | 7.25 days |  | 0% | 58 hours | 0 hours | 58 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
171 | 2.2.2.3.5 | Call Center Integration |  | 2026-06-24 11:00 | 2026-07-09 15:00 | 11.5 days |  | 0% | 86 hours | 0 hours | 86 hours |  |  | No |  |  |  |  | Medium
172 | 2.2.2.3.5.1 | NTELLI-CTI License Readiness (Customer) | 168FS | 2026-06-24 11:00 | 2026-06-25 15:00 | 1.5 days |  | 0% | 6 hours | 0 hours | 6 hours | Not Started | 173FS | No |  |  |  |  | Medium | Backlog
173 | 2.2.2.3.5.2 | Call Center Configurations and Development | 172FS | 2026-06-25 15:00 | 2026-07-09 15:00 | 10 days |  | 0% | 80 hours | 0 hours | 80 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
174 | 2.2.2.3.6 | RED 365 - F&O Integration Activities (Marked as completed due to the new approach) |  | 2026-04-13 14:00 | 2026-05-11 14:00 | 20 days |  | 100% | 128 hours | 128 hours | 0 hours |  |  | No |  |  |  |  | Medium
175 | 2.2.2.3.6.1 | RED365 - F&O Cross Functional INTERNAL Session (Integration) | 149FS | 2026-04-14 15:00 | 2026-04-16 15:00 | 2 days |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 176FS | No |  |  |  |  | Medium | Backlog
176 | 2.2.2.3.6.2 | RED365 - F&O Cross Functional Session (Integration) with customer | 175FS | 2026-04-16 15:00 | 2026-04-20 15:00 | 2 days |  | 100% | 8 hours | 8 hours | 0 hours | Not Started | 177FS | No |  |  |  |  | Medium | Backlog
177 | 2.2.2.3.6.3 | RED365 - F&O Integration GAP Preparation | 176FS | 2026-04-20 15:00 | 2026-04-23 10:00 | 2.38 days |  | 100% | 16 hours | 16 hours | 0 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
178 | 2.2.2.3.6.4 | GAP Sheet sizing & estimation | 148FS | 2026-04-13 14:00 | 2026-04-23 14:00 | 8 days |  | 100% | 64 hours | 64 hours | 0 hours | Not Started | 179FS | No |  |  |  |  | Medium | Backlog
179 | 2.2.2.3.6.5 | Integration Design Document Preparation | 178FS | 2026-04-23 14:00 | 2026-04-29 14:00 | 4 days |  | 100% | 32 hours | 32 hours | 0 hours | Not Started | 180FS, 181FS | No |  |  |  |  | Medium | Backlog
180 | 2.2.2.3.6.6 | RED 365 to F&O Integration Development (As-Is Vertical) | 179FS | 2026-04-29 14:00 | 2026-04-29 14:00 | 0 days |  | 100% |  |  |  | Not Started | 182FS | Yes |  |  |  |  | Medium | Backlog
181 | 2.2.2.3.6.7 | F&O Integration Development | 179FS | 2026-04-29 14:00 | 2026-05-04 14:00 | 3 days |  | 100% |  |  |  | Not Started | 182FS | No | F&O Team to add their estimations |  |  |  | Medium | Backlog
182 | 2.2.2.3.6.8 | RED365 - F&O Integration Testing& Fine Tuning | 180FS, 181FS | 2026-05-04 14:00 | 2026-05-11 14:00 | 5 days |  | 100% |  |  |  | Not Started | 185FS | No |  |  |  |  | Medium | Backlog
183 | 2.2.2.4 | RED 365 Deployment Activities |  | 2026-05-12 10:00 | 2026-07-27 10:00 | 54 days |  | 0% | 259 hours | 0 hours | 259 hours |  |  | No |  |  |  |  | Medium
184 | 2.2.2.4.1 | Training& UAT Preparation |  | 2026-05-12 10:00 | 2026-06-11 15:00 | 22.63 days |  | 0% | 168 hours | 0 hours | 168 hours |  | 193FS, 202FS, 199FS | No |  |  |  |  | Medium
185 | 2.2.2.4.1.1 | Environment Deployment& System Configurations (UAT) | 182FS, 136FS | 2026-05-12 10:00 | 2026-05-14 12:00 | 2.25 days |  | 0% | 18 hours | 0 hours | 18 hours | Not Started | 186FS | No |  |  |  |  | Medium | Backlog
186 | 2.2.2.4.1.2 | Receive License, Team Structure,& Team Members List from customer | 185FS | 2026-05-14 12:00 | 2026-05-25 10:00 | 6.75 days |  | 0% | 54 hours | 0 hours | 54 hours | Not Started | 187FS | No |  |  |  |  | Medium | Backlog
187 | 2.2.2.4.1.3 | Security Roles, Teams,& Departments Sheets | 186FS | 2026-05-25 10:00 | 2026-05-27 10:00 | 2 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started | 188FS | No |  |  |  |  | Medium | Backlog
188 | 2.2.2.4.1.4 | Security Roles, Teams,& Departments Config | 187FS | 2026-05-27 10:00 | 2026-05-31 12:00 | 2.25 days |  | 0% | 11 hours | 0 hours | 11 hours | Not Started | 189FS | No |  |  |  |  | Medium | Backlog
189 | 2.2.2.4.1.5 | Environment Deployment& System Fine tuning | 188FS | 2026-05-31 12:00 | 2026-06-02 12:00 | 2 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started | 190FS | No |  |  |  |  | Medium | Backlog
190 | 2.2.2.4.1.6 | User Test Script Update | 189FS | 2026-06-02 12:00 | 2026-06-09 12:00 | 5 days |  | 0% | 40 hours | 0 hours | 40 hours | Not Started | 191FS | No |  |  |  |  | Medium | Backlog
191 | 2.2.2.4.1.7 | Admin Test Script Update | 190FS | 2026-06-09 12:00 | 2026-06-11 15:00 | 2.38 days |  | 0% | 13 hours | 0 hours | 13 hours | Not Started | 193FS | No |  |  |  |  | Medium | Backlog
192 | 2.2.2.4.2 | RED365 - CE Key User Training& UAT |  | 2026-07-09 15:00 | 2026-07-27 10:00 | 11.38 days |  | 0% | 91 hours | 0 hours | 91 hours |  | 199FS | No |  |  |  |  | Medium
193 | 2.2.2.4.2.1 | Property Management Key User Training& UAT | 184FS, 191FS, 156FS, 136FS, 151FS, 160FS | 2026-07-09 15:00 | 2026-07-12 15:00 | 1 day |  | 0% | 3 hours | 0 hours | 3 hours | Not Started | 194FS | No |  |  |  |  | Medium | Backlog
194 | 2.2.2.4.2.2 | Basic Marketing/Customer Insights Journey Key User Training & UAT | 193FS | 2026-07-12 15:00 | 2026-07-13 15:00 | 1 day |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 195FS | No |  |  |  |  | Medium | Backlog
195 | 2.2.2.4.2.3 | Sales Management Key User Training& UAT | 194FS | 2026-07-13 15:00 | 2026-07-19 12:00 | 3.63 days |  | 0% | 29 hours | 0 hours | 29 hours | Not Started | 196FS | No |  |  |  |  | Medium | Backlog
196 | 2.2.2.4.2.4 | Client Relation Key User Training & UAT | 195FS | 2026-07-19 12:00 | 2026-07-21 12:00 | 2 days |  | 0% | 11 hours | 0 hours | 11 hours | Not Started | 197FS | No |  |  |  |  | Medium | Backlog
197 | 2.2.2.4.2.5 | Delivery Management Key User Training & UAT | 196FS | 2026-07-21 12:00 | 2026-07-23 10:00 | 1.75 days |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 198FS | No |  |  |  |  | Medium | Backlog
198 | 2.2.2.4.2.6 | RED365/F&O Training and UAT | 197FS | 2026-07-23 10:00 | 2026-07-27 10:00 | 2 days |  | 0% | 32 hours | 0 hours | 32 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
199 | 2.2.2.4.3 | RED 365 Q-Gate Meeting& Phase Acceptance | 184FS, 192FS | 2026-07-27 10:00 | 2026-07-27 10:00 | 0 days |  | 0% |  |  |  | Not Started | 202FS | Yes |  |  |  |  | Medium | Backlog
200 | 2.2.3 | Operation Stage |  | 2026-07-27 10:00 | 2026-08-19 13:00 | 17.38 days |  | 0% | 131 hours | 0 hours | 131 hours |  | 208FS | No |  |  |  |  | Medium
201 | 2.2.3.1 | RED365 Operation Activities |  | 2026-07-27 10:00 | 2026-08-04 13:00 | 6.38 days |  | 0% | 43 hours | 0 hours | 43 hours |  | 205FS | No |  |  |  |  | Medium
202 | 2.2.3.1.1 | RED365 - CE Production Environment Deployment& Configuration | 184FS, 199FS | 2026-07-27 10:00 | 2026-07-30 10:00 | 3 days |  | 0% | 19 hours | 0 hours | 19 hours | Not Started | 203FS | No |  |  |  |  | Medium | Backlog
203 | 2.2.3.1.2 | Upload Master Data | 202FS | 2026-07-30 10:00 | 2026-08-04 13:00 | 3.38 days |  | 0% | 24 hours | 0 hours | 24 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
204 | 2.2.3.2 | RED365 Go-live |  | 2026-08-04 13:00 | 2026-08-19 13:00 | 11 days |  | 0% | 88 hours | 0 hours | 88 hours |  |  | No |  |  |  |  | Medium
205 | 2.2.3.2.1 | Go-Live | 201FS | 2026-08-04 13:00 | 2026-08-05 13:00 | 1 day |  | 0% | 8 hours | 0 hours | 8 hours | Not Started | 206FS | No |  |  |  |  | Medium | Backlog
206 | 2.2.3.2.2 | Go-Live Support | 205FS | 2026-08-05 13:00 | 2026-08-19 13:00 | 10 days |  | 0% | 80 hours | 0 hours | 80 hours | Not Started |  | No |  |  |  |  | Medium | Backlog
207 | 2.3 | RED365 GAP Points Development |  | 2026-08-19 13:00 | 2026-09-28 10:00 | 27.63 days |  | 0% | 220 hours | 0 hours | 220 hours |  |  | No |  |  |  |  | Medium
208 | 2.3.1 | NPV Calculation | 200FS | 2026-08-19 13:00 | 2026-09-09 13:00 | 15 days |  | 0% | 120 hours | 0 hours | 120 hours | Not Started | 209FS | No |  |  |  |  | Medium | Backlog
209 | 2.3.2 | Email Notifications | 208FS | 2026-09-09 13:00 | 2026-09-15 17:00 | 4.5 days |  | 0% | 36 hours | 0 hours | 36 hours | Not Started | 210FS | No |  |  |  |  | Medium | Backlog
210 | 2.3.3 | Transfer Ownership Annex (SSRS) | 209FS | 2026-09-16 09:00 | 2026-09-17 17:00 | 2 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started | 211FS | No |  |  |  |  | Medium | Backlog
211 | 2.3.4 | Collection Case Management | 210FS | 2026-09-20 09:00 | 2026-09-21 10:00 | 1.13 days |  | 0% | 9 hours | 0 hours | 9 hours | Not Started | 212FS | No |  |  |  |  | Medium | Backlog
212 | 2.3.5 | Legal Case Management | 211FS | 2026-09-21 10:00 | 2026-09-22 10:00 | 1 day |  | 0% | 7 hours | 0 hours | 7 hours | Not Started | 213FS | No |  |  |  |  | Medium | Backlog
213 | 2.3.6 | Go-Through Session | 212FS | 2026-09-22 10:00 | 2026-09-24 10:00 | 2 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started | 214FS | No |  |  |  |  | Medium | Backlog
214 | 2.3.7 | Production Deployment after Customer Confirmation | 213FS | 2026-09-24 10:00 | 2026-09-28 10:00 | 2 days |  | 0% | 16 hours | 0 hours | 16 hours | Not Started |  | No |  |  |  |  | Medium | Backlog